# Contractor Management Software Rollout Checklist

Put a date and a name against every step in week 1. Plan on about 12 to 16 weeks for 100 to 300 contractors: a 2-week pilot, waves of about 40, then the 28-day ladder. Planning assumptions, not measured averages; reset them after the pilot.

Companion to How to Implement Contractor Management Software: A Practical Rollout Plan, www.complyflow.com/blog/how-to-implement-contractor-management-software. From ComplyFlow. Version 1.1, October 2026. A planning aid, not legal advice.

# Plan Details

| Field | Entry |
| --- | --- |
| Sponsor (decides what happens to a contractor who will not take part) | [Name] |
| Project owner (one person, protected hours) | [Name] |
| List owner | [Name] |
| Reviewers, each with a backup | [Names] |
| Site champions | [One per site] |
| Start date and latest exit date | [DD/MM/YYYY] [DD/MM/YYYY] |

# The Seven Steps

## Step 1: Decide the Scope & Name the Owners

Week 1. Owner: project owner. Done when scope, owners and baseline are written down.

☐  Sites for wave 1 chosen.

☐  Contractor types and tiers in scope chosen.

☐  Stages in scope chosen. Start with prequalification, worker documents and the gate.

☐  Sponsor, project owner, list owner, reviewers and site champions named, with backups.

☐  IT asked about email delivery and sign-in.

☐  Baseline taken: contractors listed; contractors engaged in the last 12 months; hours a week spent chasing documents; expired items found in 20 files picked at random.

## Step 2: Clean the Contractor List

Weeks 2 to 3. Owner: list owner. Done when every row has an ABN, a tier and a named contact.

☐  One row per legal entity, six columns: legal name, ABN, type of work, sites worked, tier, named contact with email.

☐  Every ABN checked on ABN Lookup (active, name matches). Duplicates merged on the ABN.

☐  Contractors not engaged in the last 12 months moved to an archive tab.

☐  Shared mailboxes replaced with a named person.

☐  Every row tiered. Rows marked "ask" resolved.

## Step 3: Set Requirements by Contractor Tier

Weeks 3 to 4. Owner: safety lead. Done when each tier is built and tested with nobody attached.

☐  For each tier, three lists written: what the company provides, what each worker provides, what a site adds.

☐  Every item has a checker, a pass rule, an expiry rule and a grace period.

☐  Lowest tier kept to the minimum.

☐  Built with nobody attached, then tested on a dummy supplier.

☐  Reviewer and backup assigned to each document type.

## Step 4: Invite Contractors in Waves

Pilot weeks 4 to 5; waves from week 6 (to week 8 for 100 contractors, week 13 for 300). Owner: administrator. Done when each wave clears before the next.

☐  Pilot of 5 to 10 contractors across the tiers, including one sole trader working from a phone. Two weeks, starting in week 4.

☐  Pilot findings fixed: requirement wording, time a reviewer takes per pack.

☐  Heads-up sent by a person the contractor already deals with: why, what it takes, the date the gate starts checking, who to call.

☐  Waves of about 40, or fewer if reviewers cannot clear that many in a week. Next wave held until the last is clearing.

☐  Invitation ladder (below) published inside the business.

## Step 5: Connect Site Sign-In to the Record

From week 5, one site at a time. Owner: site champions. Done when one site runs the gate check.

☐  A sign-in point chosen for each entry (each has its own QR code).

☐  Induction and confirmation wording agreed. Visitor setting decided.

☐  Rule decided for a worker whose record has gaps: stop them, or allow and notify.

☐  Pilot site live. Exceptions reviewed every week. Date set for switching exceptions off.

## Step 6: Train Supervisors

One hour, 1 to 2 weeks before the gate check starts. Owner: site champions.

☐  Covered: what the status means; who to call; never wave anyone through on a verbal assurance; how to log an exception; what to say.

☐  Role-played 3 cases: licence expired yesterday; missing induction; new hire not in the system.

☐  Named person at the pilot gate on the first morning. On-call contact for the first fortnight.

## Step 7: Run Old & New Side by Side

Ends about week 12 (100 contractors) or 16 (300). Owner: project owner. Done when the exit rule is met and the spreadsheet is read-only.

☐  Spreadsheet freeze date set. New contractors and renewals entered in the system only.

☐  Friday reconciliation, 15 minutes: the worker list, with what is outstanding, against who actually signed in.

☐  Exit rule written before wave 1, as a condition and a latest date (the end of the ladder on the last wave). Example: 3 consecutive weeks with nobody on site who is held only in the spreadsheet; every tier 3 contractor active; review queue empty on Fridays.

☐  Exit rule met. Spreadsheet read-only. Date recorded: [DD/MM/YYYY].

# The Invitation Ladder

| Day | Action | Who | Your rule |
| --- | --- | --- | --- |
| 0 | Invitation sent | Administrator |  |
| 5 to 7 | Reminder from the person they know | Relationship owner |  |
| 14 | Phone call | Site contact |  |
| 21 | Letter to the contractor's owner (tier 3 and above) | Sponsor |  |
| 28 | Rule applies. Low tier: escorted visitor. High tier: does not start work. | Sponsor |  |

# The Five Adoption Measures

| Measure | Week 1 | Week 4 | Week 8 | Target (set after the pilot) |
| --- | --- | --- | --- | --- |
| 1. Activation at day 14: invited companies that have started their record |  |  |  |  |
| 2. First-pass approval rate: documents approved without being sent back |  |  |  |  |
| 3. Gate exceptions per week |  |  |  |  |
| 4. Leakage: documents still arriving by email |  |  |  |  |
| 5. Admin hours per week spent chasing |  |  |  |  |